## Cover
AIO REGRESSION TEST CASES
Version:
Issue date:
Project Suite:
Project Name:	WCM 1.2.x
Total Cases:	50
Test Status:	Passed: Test is OK / Blocked: Could not run the test (another bug is blocking) / Failed: Test failed, a bug is entered on it (please add the bug ID) / N/A: Test is not possible to run on this version

Record of change:
Effective Date	Version	Change description	Originator	Reviewer/ / Approver	Reference
04/Oct/10		AIO split to products	minh.nguyen
20/Oct/10		ALL-411 / CCP-496	minh.nguyen
		Missing: (technique) / - ECM-5458 / - Portal-3755 / - CS-4197 / - CS-4426 / - KS-2610 / - CS-4412 / - JCR-1411 / - WCM-2859 / - KS-2399 / - JCR-1401 / - Portal- 3814 / - WCM-2796 / - CCP-411 / - WCM-2815
29/Nov/2010		Remove: / - CCP-483 (Do not allow to add document with name contain special characters)	an_Nguyen
27/Dec/2010		remove: / - REG_WCM_WCM-006 (There is no tab Illustration in Content Detail anymore )	an_Nguyen

## Check_List
Check List / Based on Product built version:		BugID	Priority
Id	Main cases	Priority	Priority
Bugs on version 1.6.5
REG_WCM_CCP-147	Can not download an uploaded document in PCV portlet	WCM-2157, SST-186, CCP-184	High
REG_WCM_CCP-346	Check if the content edition is considered after publication	WCM-2727	High
REG_WCM_CCP-345	Cache & Categories with publication errors	WCM-2725	High
REG_WCM_CCP-386	Check if Newsletter mail's validator allows a multiple domain names in address mail	WCM-2782	High
REG_WCM_CCP-329	Check when publish content after image resize with Shift button pressed	ALL-295, WCM-2715, PORTAL-3783	High
REG_WCM_CCP-384	Label categories are not traduced in clv edition	WCM-2787, WCM-2781, WCM-2786	High
REG_WCM_CCP-247	Check viewing localised content	WCM-2628	High
REG_WCM_CCP-377	Check translation of results' number after search	ALL-328, WCM-2757	Low
REG_WCM_CCP-373	Search result - wrong traduction when there's no result	ALL-327, WCM-2754	Low
REG_WCM_CCP-374	Check translation of label in the “Form Generator” portlet	WCM-2755	Low
REG_WCM_CCP-300	Mistakes in french internationalization	WCM-2687	High
REG_WCM_CCP-347	Check Sorting Mechanism	WCM-2728	High
REG_WCM_CCP-302	Check encoding when display Taxonomy in the CLV categories	WCM-2688, WCM-2627, PORTAL-3744	High
REG_WCM_CCP-359	Check showing webcontent by category (presentation portlet)	WCM-2744	High
REG_WCM_CCP-360	Check Manage taxonomy	WCM-2745	High
REG_WCM_CCP-368	Error while setting a page with PCLV portlet	WCM-2753	High
REG_WCM_CCP-362	Check Problem in downloading binary from PCLV	WCM-2746	High
REG_WCM_CCP-332	Check Problem with "Add a site page link " on FCKEDITOR	WCM-2717	Low
REG_WCM_CCP-344	Check play a media file that was published into a page	WCM-2723	Low
REG_WCM_CCP-392	Check listing content to be displayed in SCV when switch the filter condition	WCM-2788	Low
REG_WCM_CCP-328	Check display a link in a content	WCM-2227	High
REG_WCM_CCP-371	Check when select content from search result to view in CLV	WCM-2751	High
REG_WCM_CCP-343	Inversion of content's list in CLV at every validation	WCM-2721	High
REG_WCM_CCP-303	Changes in FCC action's parameters are not taken in consideration	WCM-2689, ECM-5237	High
REG_WCM_CCP-426	Searched texts in search results are not highlighted	WCM-2822
Bugs on version 1.6.6
REG_WCM_ALL-362	Check Homepage button on Start bar	WCM-2807	Low
REG_WCM_CCP-422	A problem with clv when browsing directories with special characters (using IE7)	WCM-2816	High
REG_WCM_CCP-405	Check listing document with special character in name in CLV	WCM-2795	High
REG_WCM_CCP-424	Check order content in CLV using manual browse	WCM-2818	High
REG_WCM_CCP-429	Check when search result exceeds 250	WCM-2828	High
REG_WCM_WCM-001	Check if there's icon to Edit/Delete comment on document	WCM-2852	Low
REG_WCM_CCP-474	Check internationalized label in WCMInsertContent functionality	WCM-2853	Low
REG_WCM_CCP-459	Check if links Next & Previous in search portlet are internationalized	WCM-2844	Low
REG_WCM_CCP-454	Check insert link to a site page when add new web content	WCM-2843	High
REG_WCM_WCM-002	Check showing Backup path in Manage Publication form	WCM-2856	Low
REG_WCM_CCP-483	Check when move document contain illegal jcr character	WCM-2858	High
REG_WCM_CCP-453	Check showing sub node on admin bar when parent does not select to any page	WCM-2842	High
REG_WCM_CCP-404	Impossible to download a binary file with name containing an illegal jcr char (using the right popup menu)	WCM-2832	Low
REG_WCM_CCP-496	Check WCMInsertContent when browsing directories with special characters	WCM-2861	High
REG_WCM_CCP-495	Check search with accented characters	WCM-2860	High
REG_WCM_CCP-418	Check removing container from page	WCM-2821	High
REG_WCM_CCP-514	Check Edit CLV in manual mode	WCM-2863	Low
REG_WCM_WCM-003	Check showing uploaded file with illegal JCR characters in Name in Sites Explorer	WCM-2791	High
REG_WCM_CCP-403	Check showing uploaded file with illegal JCR characters in Name in Manage Publication form	WCM-2791	High
REG_WCM_WCM-004	Check when click Edit icon of Content Detail portlet while adding new page	WCM-2887	High
REG_WCM_WCM-005	Check add new Category in Newsletter Manager	WCM-2840	Low
REG_WCM_CCP-443	Check when drag & drop container into page	WCM-2883	High
REG_WCM_CCP-465	Portlet Category Navigation	WCM-2845	High
Bugs on version 1.6.7
REG_WCM_WCM-007	Check mini calendar when add newsletter	ALL-411	High
Bugs on version 1.6.8
REG_WCM_CCP-404	Download a binary file with name containing an illegal jcr char (using the right popup menu)	WCM-2832	High
REG_WCM_CCP-465	Portlet Category Navigation	WCM-2845	High
REG_WCM_CCP-368	Error while setting a page with PCLV portlet	WCM-2753	High
REG_WCM_CCP-524	Link still be referenced after being inserted	WCM-2872	High
REG_WCM_CCP-668	Duplicated portlet ID: Content List, Category Navigation, Category Content, Content by URL	WCM-2936	High
REG_WCM_CCP-707	Newsletter Wrong text of changing "Subscribe" in French	WCM-2952	High
REG_WCM_CCP-668	No attribute "target" in "ACME Overview" when checking with W3C	WCM-2939	High
REG_WCM_WCM-2929	Hard-coded labels in French	WCM-2929	High
REG_WCM_CCP-704	Impossible selection to insert contents into a text content	WCM-2951	High
REG_WCM_CCP-588	FCKEditor: Exception when creating page link after adding new page for the user navigation	WCM-2914	High
REG_WCM_CCP-586	CLV manual search content: Error when previewing content with image loaded from JCR	WCM-2911	High
REG_WCM_CCP-720	Add page wizards: Some labels are not translated in French	WCM-2957	High
REG_WCM_CCP-639	The selection of repository brings up some content	WCM-2952	High
REG_WCM_CCP-731	Impossible to select an invisible page when creating a portal page link into a text (FCK Editor)	WCM-2960	High
REG_WCM_CCP-677	Error in displaying .rtf file	WCM-2943	High

## Bugs_v1.6.5
	TEST CASES					Passed	0
				Failed	0
	Function List:	Bugs on WCM 1.2.x for regression test					Blocked	0
	Total Main Cases:	25					Untested	0
				N/A	0
Case No	Related function	Case ID	Path	Case Description	Step Description	Steps to produce	Expected Output	Priority	Link	Bug description
001	REG_WCM_CCP-147	001	WCM/REG_WCM_CCP-147	Can not download an uploaded document in PCV portlet	Step 1: Upload file	- Go to Site Explorer, ACME drive / - Upload a file (pdf for example) in a category	Upload file successfully	High	WCM-2157, SST-186, CCP-184	Upload a file (pdf for example) in a category
	REG_WCM_CCP-147	001	WCM/REG_WCM_CCP-147	Can not download an uploaded document in PCV portlet	Step 2: View uploaded file in News page	- Choose News page on ACME site / - Select category to view the uploaded file before / - Click to open the previously uploaded document / - Click Download this file link	Download file successfully	High	WCM-2157, SST-186, CCP-184
002	REG_WCM_CCP-346	001	WCM/REG_WCM_CCP-346	Check if the content edition is considered after publication	Step 1: Create a free layout web content	- Login by admin / - Go to Contents Explorer → Site Management / - Select 1 node & click Add document / - Select Free layout web content template & input valid value for field / - Click Save	New Free layout web content is created	High	WCM-2727	After step 6: go to /classic/home ==> old content is shown instead of new one (in edit mode you can see the new content)
	REG_WCM_CCP-346	001	WCM/REG_WCM_CCP-346	Check if the content edition is considered after publication	Step 2: Edit content	- Select new added web content / - Click Edit document in Action bar / - Make changes for the web content	Changes are saved	High	WCM-2727
	REG_WCM_CCP-346	001	WCM/REG_WCM_CCP-346	Check if the content edition is considered after publication	Step 3: Edit status to publish	- Click Manage Publication from Action bar / - Click Live to change status	Change status successfully (Enrolled is marked)	High	WCM-2727
	REG_WCM_CCP-346	001	WCM/REG_WCM_CCP-346	Check if the content edition is considered after publication	Step 4: Add node to a page (/classic/home for example)	- Choose Publication Pages tab / - Select page from left pane then click → button	Path of selected page is displayed in right pane & the web content is displayed in selected page	High	WCM-2727
	REG_WCM_CCP-346	001	WCM/REG_WCM_CCP-346	Check if the content edition is considered after publication	Step 5: Edit content again	In Content Explorer: edit content of above web content	Changes is saved (status of current version is draft)	High	WCM-2727
	REG_WCM_CCP-346	001	WCM/REG_WCM_CCP-346	Check if the content edition is considered after publication	Step 6: Publish the node again	In Content Explorer: / - Click Manage Publication / - Click Live to change status	go to /classic/home: the content is updated with the new edited (both view/edit mode)	High	WCM-2727
003	REG_WCM_CCP-345	001	WCM/REG_WCM_CCP-345	Cache & Categories with publication errors	Step 1: Create web content	- Go to Content Explorer / - Select 1 personal drive (e.g: public) / - Create 1 free layout web content	Create new web content successfully	High	WCM-2725	Currently at step 8 the change in the web content is not updated (display the old content)
	REG_WCM_CCP-345	001	WCM/REG_WCM_CCP-345	Cache & Categories with publication errors	Step 2: Edit content	- Select then change content of new added web content	Edit successfully	High	WCM-2725
	REG_WCM_CCP-345	001	WCM/REG_WCM_CCP-345	Cache & Categories with publication errors	Step 3: Public node	go to manage publications and choose States and versions based publication: make the node published	Public node successfully	High	WCM-2725
	REG_WCM_CCP-345	001	WCM/REG_WCM_CCP-345	Cache & Categories with publication errors	Step 4: Add reference	- Click Manage categories from Action bar / - Select “acme” from Taxonomy Tree / - Choose World, Business, Technology ,Sports	Selected taxonomies are listed in Referenced categories tab	High	WCM-2725
	REG_WCM_CCP-345	001	WCM/REG_WCM_CCP-345	Cache & Categories with publication errors	Step 5: View added content	- Choose News page in acme site / - Click World / (do not open other categories)	the node test exist: open it : content 0000 is shown	High	WCM-2725
	REG_WCM_CCP-345	001	WCM/REG_WCM_CCP-345	Cache & Categories with publication errors	Step 6: Edit content of web content	- Go to Public drive / - Edit added web content above (change the content)	Change is saved	High	WCM-2725
	REG_WCM_CCP-345	001	WCM/REG_WCM_CCP-345	Cache & Categories with publication errors	Step 7: Publish edited content	- Click Manage Publication & Click State	Change is saved	High	WCM-2725
	REG_WCM_CCP-345	001	WCM/REG_WCM_CCP-345	Cache & Categories with publication errors	Step 8: Check displaying change of the web content	- Go to News page in acme site & choose World category / - Open the web content from right pane	The web content details is shown with new changes in content (new content is updated in other category)	High	WCM-2725
004	REG_WCM_CCP-386	001	WCM/REG_WCM_CCP-386	Check if Newsletter mail's validator allows a multiple domain names in address mail	Step 1: Show Newsletters page	Go to Acme->newsletters	Newsletters page is shown correctly	High	WCM-2782	A Popup appears with Email address is invalid! message.
	REG_WCM_CCP-386	001	WCM/REG_WCM_CCP-386	Check if Newsletter mail's validator allows a multiple domain names in address mail	Step 2: Subscribe mail	- Input value into "Your Email" field like: user@domain1.domain2.fr / - Tick the check-box corresponding to your chosen subscription / - Click Subscribe	Show popup alert subscribe mail successfully	High	WCM-2782
005	REG_WCM_CCP-329	001	WCM/REG_WCM_CCP-329	Check when publish content after image resize with Shift button pressed	Step 1: Create new content with image	- Go to Site Explorer / - Go to acme/web content / - Click Add document in action bar / - Select 1 template / - Input valid value for fields / - In the CK Editor: Click WCM Content Selector / - Select path from left pane / - Upload 1 image / - Select uploaded image to add into the web content / - Save	New web content added with image	High	ALL-295, WCM-2715, PORTAL-3783	IE 7 crash when publishing content after image resize with Shift button pressed
	REG_WCM_CCP-329	001	WCM/REG_WCM_CCP-329	Check when publish content after image resize with Shift button pressed	Step 2: Resize the image	- Select added web content to view / - Click Edit document / - Resize the image / - Click Save	The image in the content is resized	High	ALL-295, WCM-2715, PORTAL-3783
006	REG_WCM_CCP-384	001	WCM/REG_WCM_CCP-384	Label categories are not traduced in clv edition	Step 1: Change language	Go to Language Setting & select 1 language to display	The site is displayed in new selected language	High	WCM-2787, WCM-2781, WCM-2786	Categories' labels are not translated in CLV edition:
	REG_WCM_CCP-384	001	WCM/REG_WCM_CCP-384	Label categories are not traduced in clv edition	Step 2: Show CLV config form	- Go to Site Editor --> Add Page Wizard / - Input valid value then go to step 3 in wizard / - Drag & drop Content List portlet into page / - Click Edit portlet icon	CLV config form is shown	High	WCM-2787, WCM-2781, WCM-2786
	REG_WCM_CCP-384	001	WCM/REG_WCM_CCP-384	Label categories are not traduced in clv edition	Step 3: Check displaying label in new selected language	- Choose Manual mode then click + icon to Select folder part	The every label is well translated	High	WCM-2787, WCM-2781, WCM-2786
007	REG_WCM_CCP-247	001	WCM/REG_WCM_CCP-247	Check viewing localised content	Step 1: Add view into Site Explorer	- Login by admin / - Go to Site Administrator / - Manage drive / - Edit 1 drive that you are going to use (e.g: Manage site): add more view (admin view, simple view, system view)	Edit successfully	High	WCM-2628	when i try to view the content in translated language i get the following error in the console: / [ERROR] portal:Lifecycle - template : /exo:ecm/templates/exo:webContent/views/vi / ew1 <javax.jcr.PathNotFoundException: Node not found /sites content/live/redhat/ / web contents/News/languages/fr/default.html/jcr:content>javax.jcr.PathNotFoundEx / ception: Node not found /sites content/live/redhat/web contents/News/languages/f / r/default.html/jcr:content
	REG_WCM_CCP-247	001	WCM/REG_WCM_CCP-247	Check viewing localised content	Step 2: Add content	Go to Content Explorer -> Sites Management under /acme create new content	Add new content successfully	High	WCM-2628
	REG_WCM_CCP-247	001	WCM/REG_WCM_CCP-247	Check viewing localised content	Step 3: Set localize for added content	- Select to view added content / - Go to Collaboration → Add/edit localized contents from Action bar / - Select new language & input valid value for field in new selected language	New added language is listed in Language drop down list in View Language tab	High	WCM-2628
	REG_WCM_CCP-247	001	WCM/REG_WCM_CCP-247	Check viewing localised content	Step 4: View content in new language	- Choose new added language from list then click View	The content is display well in selected language	High	WCM-2628
008	REG_WCM_CCP-377	001	WCM/REG_WCM_CCP-377	Check translation of results' number after search	Step 1: Change language	- Go to Language Settings & select a language to view	The site is displayed in new selected language	Low	ALL-328, WCM-2757	When you make a search which results take many pages, the message at right top is not correctly translated in French. / "Résultats 1 - 5 d'environ 35 pour test (0.079 seconde)" should be "Résultats 1 - 5 sur 35 pour test (0.079 seconde) "
	REG_WCM_CCP-377	001	WCM/REG_WCM_CCP-377	Check translation of results' number after search	Step 2: Search	Make a search which results take many pages by input text into quick search textbox & enter	The message at right top is correctly in new selected language	Low	ALL-328, WCM-2757
009	REG_WCM_CCP-373	001	WCM/REG_WCM_CCP-373	Search result - wrong traduction when there's no result	Step 1: Change language	- Go to Language Settings & select a language to view	The site is displayed in new selected language	Low	ALL-327, WCM-2754	When a search has no result, the traduction for message is wrong (no_result.png). / It is : Votre recherche ijij - ne correspond à aucun documentandpage / It should be : Votre recherche ijij - ne correspond à aucun document et page
	REG_WCM_CCP-373	001	WCM/REG_WCM_CCP-373	Search result - wrong traduction when there's no result	Step 2: Search	Make a search that return no result	Message is display correctly	Low	ALL-327, WCM-2754
010	REG_WCM_CCP-374	001	WCM/REG_WCM_CCP-374	Check translation of label in the “Form Generator” portlet	Step 1: Change language	- Go to Language Settings & select a language to view	The site is displayed in new selected language	Low	WCM-2755	The title of the tab should be "Constructeur de formulaire" instead of "Formulaire de constructeur".
	REG_WCM_CCP-374	001	WCM/REG_WCM_CCP-374	Check translation of label in the “Form Generator” portlet	Step 2: Show “Form Generator” portlet	Go to Groups → Form Generator	The labels are well translated	Low	WCM-2755
011	REG_WCM_CCP-300	001	WCM/REG_WCM_CCP-300	Mistakes in french internationalization	Step 1: Check translation of label in some forms when add new SCV	- Go to Language Setting then select a language to display / - Go to Site Editor --> Add content	Add new content form is shown. Do some next steps to complete adding new SCV to check if all labels are well translated in selected language	High	WCM-2687	Add SCV welcome form: / Abort = Annuler / Bienvenue à SCV = Bienvenue dans SCV / Créer de nouveaux contenus = Créer un nouveau contenu / Add SCV select layout form: / Abort = Annuler / Sous forme de modèle = Suivant un modèle / Ideally: translate the labels in the layout selectbox / Newsletter Manager/Add new category form: / Redactor = Rédacteur / Save = Enregistrer / Cancel = Annuler / Add Newsletter form: / Advanced=Avancé
	REG_WCM_CCP-300	001	WCM/REG_WCM_CCP-300	Mistakes in french internationalization	Step 2: Check translation of label in Add new subscription form (Newsletter)	- Go to Newsletter Manager / - Click New subscription	Add new subscription form is shown with all labels are well translated in selected language	High	WCM-2687
	REG_WCM_CCP-300	001	WCM/REG_WCM_CCP-300	Mistakes in french internationalization	Step 3: Check translation of label in Add new letter form	- Go to Newsletter Manager / - Click Newsletter	Add new letter form is shown with all label are well translated in selected language	High	WCM-2687
012	REG_WCM_CCP-347	001	WCM/REG_WCM_CCP-347	Check Sorting Mechanism	Step 1: Create node	- Login by admin / - Go to Site Explorer → Site Management / - Create a folders and documents list	Create successfully	High	WCM-2728	Currently: / stack-trace / /////////// / javax.jcr.RepositoryException: Unknown type -1 / at org.exoplatform.ecm.webui.comparator.PropertyValueComparator.compare(PropertyValueComparator.java:70) / at
	REG_WCM_CCP-347	001	WCM/REG_WCM_CCP-347	Check Sorting Mechanism	Step 2: Sort the list	- Sort the list (by title, date, author, status)	Sort successfully	High	WCM-2728
013	REG_WCM_CCP-302	001	WCM/REG_WCM_CCP-302	Check encoding when display Taxonomy in the CLV categories	Step 1: Add new taxonomy tree	- Go to Site administration. / - Go to Ontologies then Manage Taxonomy Trees. / - Click Edit icon at the line of “acme” / - Click Add to add new taxonomy under the acme with name contains accented character like "prévention".	Create new taxonomy tree successfully	High	WCM-2688, WCM-2627, PORTAL-3744	Currently display error of the header at step 4
	REG_WCM_CCP-302	001	WCM/REG_WCM_CCP-302	Check encoding when display Taxonomy in the CLV categories	Step 2: Check the displaying the name of new added taxonomy	- Go to the News page in the acme site and click on the category just created	The name of the category is displayed OK in the header	High	WCM-2688, WCM-2627, PORTAL-3744
014	REG_WCM_CCP-359	001	WCM/REG_WCM_CCP-359	Check showing webcontent by category (presentation portlet)	Step 1: Add new taxonomy tree	- Login as admin (root) / - Go to Sites Administration ->Manage Taxonomy Trees / - Click Edit icon at acme line / - Click Add icon in Action column / - Input Name for new taxonomy & click Save (under acme add new taxonomy tree.) / - Click close the Edit taxonomy tree form	New taxonomy tree is added successfully under the acme	High	WCM-2744	After step 4: The content is not exist in this page and we got an exception
	REG_WCM_CCP-359	001	WCM/REG_WCM_CCP-359	Check showing webcontent by category (presentation portlet)	Step 2: Add new content in Site Explorer	- Go to Site explorer and then Sites management / - Select acme node from left pane / - Click Add document / - Select 1 web content template / - Input needed value in fields (the name must begin with "acme" for example type "acmeexample" as name.) / - Click Save	New content is added	High	WCM-2744
	REG_WCM_CCP-359	001	WCM/REG_WCM_CCP-359	Check showing webcontent by category (presentation portlet)	Step 3: Add referenced category to new added web content	- Select to view new added content / - Click Manages Categories from Action bar then choose Select category tab / - Select acme from Taxonomy Tree drop down list / - Click icon in Action column at the line of new added taxonomy at Step 1 / - Click Close	- Selected taxonomy is listed in Referenced categories tab in Add category form	High	WCM-2744
	REG_WCM_CCP-359	001	WCM/REG_WCM_CCP-359	Check showing webcontent by category (presentation portlet)	Step 4: View new added taxonomy at Step 1 in News page	Go to ACME site and select News page and then click on created category	The web content created above is displayed in right pane & there's no error in console	High	WCM-2744
015	REG_WCM_CCP-360	001	WCM/REG_WCM_CCP-360	Check Manage taxonomy	Step 1: Add new taxonomy tree	- Login as admin (root) / - Go to Sites Administration ->Manage Taxonomy Trees / - Click Edit icon at acme line / - Click Add icon in Action column / - Input Name for new taxonomy / Must begin with "acme" for example put as name "acmetest". / - Click Save / - Click Close the Edit taxonomy tree form	New taxonomy tree is added successfully under the acme	High	WCM-2745	After step 3: “acme” is listed in the Referenced categories tab in stead of “acmetest” / (=>this content will be created under acme and not acmetest. / under /acme/categories/acme we will find this content .)
	REG_WCM_CCP-360	001	WCM/REG_WCM_CCP-360	Check Manage taxonomy	Step 2: Add new content in Site Explorer	- Go to Site explorer and then Sites management / - Select acme node from left pane / - Click Add document / - Select 1 web content template / - Input valid value for fields / - Click Save	New content is added	High	WCM-2745
	REG_WCM_CCP-360	001	WCM/REG_WCM_CCP-360	Check Manage taxonomy	Step 3: Add referenced category to new added web content	- Select to view new added content / - Click Manages Categories from Action bar then choose Select category tab / - Select acme from Taxonomy Tree drop down list / - Click icon in Action column at the line of new added taxonomy at Step 1	- Selected taxonomy is listed in Referenced categories tab in Add category form	High	WCM-2745
016	REG_WCM_CCP-368	001	WCM/REG_WCM_CCP-368	Error while setting a page with PCLV portlet	Step 1: View News page	- Login as admin / - Go to ACME site -> Select News page.	News page is displayed	High	WCM-2753	Currently at step 6 the Edit mode tab is blank, we cannot setting a new taxonomy tree. / And we got an exception
	REG_WCM_CCP-368	001	WCM/REG_WCM_CCP-368	Error while setting a page with PCLV portlet	Step 2: Show Edit page wizard	Go to Site Editor ->Edit Page.	Edit page wizard is shown currently at step 3	High	WCM-2753
	REG_WCM_CCP-368	001	WCM/REG_WCM_CCP-368	Error while setting a page with PCLV portlet	Step 3: Edit page	- Click x icon at PCLV portlet (Parameterized) to delete it from this page / - Click Save to complete editing page	Edit page successfully	High	WCM-2753
	REG_WCM_CCP-368	001	WCM/REG_WCM_CCP-368	Error while setting a page with PCLV portlet	Step 4: Delete acme category	Go to Site Explorer -> Sites Management under /acme/categories delete the acme category	acme category is deleted	High	WCM-2753
	REG_WCM_CCP-368	001	WCM/REG_WCM_CCP-368	Error while setting a page with PCLV portlet	Step 5: Show Edit page wizard form again	- Select News page in acme site / - Select News page -> Site Editor -> Edit Page Wizard.	Edit page wizard is shown currently at step 2	High	WCM-2753
	REG_WCM_CCP-368	001	WCM/REG_WCM_CCP-368	Error while setting a page with PCLV portlet	Step 6: Add PCLV portlet into page & config	- Drag & drop Category content portlet / - Click Edit portlet icon	Parameterized content list viewer configuration form is shown in Edit mode tab	High	WCM-2753
017	REG_WCM_CCP-362	001	WCM/REG_WCM_CCP-362	Check Problem in downloading binary from PCLV	Step 1: Upload a binary	- Go to Site Explorer --> Site Management / - Upload 1 binary (.pdf) in to a category	Upload file successfully	High	WCM-2746	# try to download it, oups, you can not, the link points to jcr:frozeNode / # Go in Edit_MODE, and try to download the document / # It is working, the file is downloaded
	REG_WCM_CCP-362	001	WCM/REG_WCM_CCP-362	Check Problem in downloading binary from PCLV	Step 2: Change status to public	- Select uploaded file / - Click Manage Publication / - Change to Live	Change status successfully (Enrolled is marked)	High	WCM-2746
	REG_WCM_CCP-362	001	WCM/REG_WCM_CCP-362	Check Problem in downloading binary from PCLV	Step 3: Add referenced category	- Choose Manage category from Action bar and add it into a category (e.g:acme/World)	Add success	High	WCM-2746
	REG_WCM_CCP-362	001	WCM/REG_WCM_CCP-362	Check Problem in downloading binary from PCLV	Step 4: View the uploaded content in page	- Choose News page in acme site / - Choose category at step 3 (World) / - Click to view the uploaded file in the right pane	The file is shown	High	WCM-2746
	REG_WCM_CCP-362	001	WCM/REG_WCM_CCP-362	Check Problem in downloading binary from PCLV	Step 5: Down load file	Click on Download this file link	The file is downloaded	High	WCM-2746
018	REG_WCM_CCP-332	001	WCM/REG_WCM_CCP-332	Check Problem with "Add a site page link " on FCKEDITOR	Step 1: Show form to edit SCV portlet	- Login by root / - Go to acme site / - Turn on edit mode / - Click Edit icon at 1 SCV portlet (e.g: banner)	Edit form is shown	Low	WCM-2717	With Firefox every thing works well but with Internet Explorer 8 the href area is very short and it's difficult to find where to click
	REG_WCM_CCP-332	001	WCM/REG_WCM_CCP-332	Check Problem with "Add a site page link " on FCKEDITOR	Step 2: Show form to Insert link to site page	In the FCKEDITOR: click the icon Insert link to site page	The form is well displayed	Low	WCM-2717
019	REG_WCM_CCP-344	001	WCM/REG_WCM_CCP-344	Check play a media file that was published into a page	Step 1: Upload file	- Go to Site Explorer --> Site Management / - Upload 1 media file into a category (/classic/medias/videos/)	Upload file successfully	Low	WCM-2723	The file can not be opened
	REG_WCM_CCP-344	001	WCM/REG_WCM_CCP-344	Check play a media file that was published into a page	Step 2: Public file	- Select uploaded file / - Choose Manage Publication then change status to Live / - In Publication pages tab: select 1 page to public this file	Public file successfully	Low	WCM-2723
	REG_WCM_CCP-344	001	WCM/REG_WCM_CCP-344	Check play a media file that was published into a page	Step 3: Check using published file in page	- Open selected page at step 2 / - Try to play the media file	The file is done	Low	WCM-2723
020	REG_WCM_CCP-392	001	WCM/REG_WCM_CCP-392	Check listing content to be displayed in SCV when switch the filter condition	Step 1: Create folder	- Go in the Content Explore and create a folder	Folder is created	Low	WCM-2788	The content in the right pane is not updated, user have to click on the folder again to see it
	REG_WCM_CCP-392	001	WCM/REG_WCM_CCP-392	Check listing content to be displayed in SCV when switch the filter condition	Step 2: Create web content	- Select added folder & add 1 content (document) into it	Content is added	Low	WCM-2788
	REG_WCM_CCP-392	001	WCM/REG_WCM_CCP-392	Check listing content to be displayed in SCV when switch the filter condition	Step 3: Upload file	- Upload 1 file into above folder	Upload file successfully	Low	WCM-2788
	REG_WCM_CCP-392	001	WCM/REG_WCM_CCP-392	Check listing content to be displayed in SCV when switch the filter condition	Step 4: Add SCV page	- Go to Site Editor --> Add page wizard / - At step 3: drag & drop Single Content Viewer portlet into page	Drag & drop successfully	Low	WCM-2788
	REG_WCM_CCP-392	001	WCM/REG_WCM_CCP-392	Check listing content to be displayed in SCV when switch the filter condition	Step 5: Edit SCV portlet	- Click Edit icon to edit SCV portlet	Edit form is shown	Low	WCM-2788
	REG_WCM_CCP-392	001	WCM/REG_WCM_CCP-392	Check listing content to be displayed in SCV when switch the filter condition	Step 6: Config SCV by selecting exiting content	- In Welcome to Single Content Viewer form: choose Select a content / - In the Content Browser tab: select path to added folder at step 1	The content created at step 2 is listed in right pane	Low	WCM-2788
	REG_WCM_CCP-392	001	WCM/REG_WCM_CCP-392	Check listing content to be displayed in SCV when switch the filter condition	Step 7: Switch the filter	Switch the filter by selecting Media for Filter by	The content listed in right pane is replaced by the uploaded file at step 3	Low	WCM-2788
021	REG_WCM_CCP-328	001	WCM/REG_WCM_CCP-328	Check display a link in a content	Step 1: Create content	- Go to Site Explorer --> Site management / - Select a category & create 1 document with link in content	Create new content successfully	High	WCM-2227	The link is display without underline
	REG_WCM_CCP-328	001	WCM/REG_WCM_CCP-328	Check display a link in a content	Step 2: View added content	Select added content to view	The link in the content is display with the underline	High	WCM-2227
022	REG_WCM_CCP-371	001	WCM/REG_WCM_CCP-371	Check when select content from search result to view in CLV	Step 1: Show form to edit CLV portlet	- Select Home page in acme site / - Turn on edit mode / - Click Preference icon at a CLV (Documents or Latest News)	Edit form is shown	High	WCM-2751	error in UI after step 4
	REG_WCM_CCP-371	001	WCM/REG_WCM_CCP-371	Check when select content from search result to view in CLV	Step 2: Show form to select path	- Choose the By content / - Click on the select folder path icon	Multiple Content Select panel is shown	High	WCM-2751
	REG_WCM_CCP-371	001	WCM/REG_WCM_CCP-371	Check when select content from search result to view in CLV	Step 3: Select content	- Select a content from the content browser / - Save	Selected content is listed	High	WCM-2751
	REG_WCM_CCP-371	001	WCM/REG_WCM_CCP-371	Check when select content from search result to view in CLV	Step 4: Search content	- Click on the select folder path icon again / - Use content search form tab to search on content / -Choose the search result to introduce it in the content list	Chosen content from search result is listed	High	WCM-2751
023	REG_WCM_CCP-343	001	WCM/REG_WCM_CCP-343	Inversion of content's list in CLV at every validation	Step 1: Create document	- Go to site Explorer → Site Management / - Create some documents (doc1, doc2, doc3)	Create document successfully	High	WCM-2721	1/Create a page and include a Portlet CLV in it. / 2/Configure the CLV in manual mode and add in it 3 documents: Doc1,Doc2 and Doc3 / 3/Validate the CLV+ the page / => The CLV shows these documents in this order: Doc3, Doc2 and Doc3, but, it is expected to have :Doc1, Doc2 and Doc 3 / * / Using now the edit mode and edit the CLV =>the list appears in this order: Doc3, Doc2, Doc1. But, if you validate (without modifying neither the order, nor anything else), this same list appears in this order: Doc1, Doc2, Doc3
	REG_WCM_CCP-343	001	WCM/REG_WCM_CCP-343	Inversion of content's list in CLV at every validation	Step 2: Create page	Create a page includes a Portlet CLV in it.	Create new page successfully	High	WCM-2721
	REG_WCM_CCP-343	001	WCM/REG_WCM_CCP-343	Inversion of content's list in CLV at every validation	Step 3: List added document into created page	- Turn on edit mode / - Click Quick Edit icon to show Edit above CLV portlet in added page / - Choose Manual mode & click + icon to show form to select document / - Select category that contain created documents at step 1 / - Choose document to displayed from right pane / - Click Save	Selected documents are listed (by order: doc1, doc2, doc3)	High	WCM-2721
	REG_WCM_CCP-343	001	WCM/REG_WCM_CCP-343	Inversion of content's list in CLV at every validation	Step 4: Change the order be documents that will be displayed	- Click Edit icon again / - Do not make any change / - Click Save	The order of document has no change	High	WCM-2721
024	REG_WCM_CCP-303	001	WCM/REG_WCM_CCP-303	Changes in FCC action's parameters are not taken in consideration	Step 1: Add FCC page	- Go to Site Editor --> Add New Page / - At step 3: Drag & drop FCC portlet into page	FCC portlet is displayed in right pane at step 3	High	WCM-2689, ECM-5237	When executing the FCC, sendMailAction took the first mail added as send mail to parameter . / The new values are taken in consideration after restarting the server.
	REG_WCM_CCP-303	001	WCM/REG_WCM_CCP-303	Changes in FCC action's parameters are not taken in consideration	Step 2: Config FCC	- Click Edit at the top right corner of FCC portlet / - Select locate to save is Group/platforms/users/documents / - Click on Add Action icon / - Add “exo:SendMailAction” with a specific email address (mail1) (Life cycle: add) / - Click Save to complete adding new page	Add action successfully	High	WCM-2689, ECM-5237
	REG_WCM_CCP-303	001	WCM/REG_WCM_CCP-303	Changes in FCC action's parameters are not taken in consideration	Step 3: Add document using FCC	In new added FCC page: Input valid values & click Save to add new document	An email is sent to registered email (mail 1) when add action	High	WCM-2689, ECM-5237
	REG_WCM_CCP-303	001	WCM/REG_WCM_CCP-303	Changes in FCC action's parameters are not taken in consideration	Step 4: Change registered email	- Edit FCC portlet again --> Edit added action with new email address (mail2)	Change is saved	High	WCM-2689, ECM-5237
	REG_WCM_CCP-303	001	WCM/REG_WCM_CCP-303	Changes in FCC action's parameters are not taken in consideration	Step 5: Check sending mail after editing FCC	Use FCC page to create another document	An email is sent to new-registered email (mail 2)	High	WCM-2689, ECM-5237
025	REG_WCM_CCP-426	001	WCM/REG_WCM_CCP-426	Check if Searched texts in search results are highlighted	Step 1: Search	- Login / - Input text in search text box in the top right screen / - Hit the enter	- The result is returned / - The search keyword is highlighted in the result	High	WCM-2822

## Bugs_v1.6.6
	TEST CASES					Passed	0
				Failed	0
	Function List:	Bugs on WCM 1.2.x for regression test					Blocked	0
	Total Main Cases:	25					Untested	0
				N/A	0
Case No	Related function	Case ID	Path	Case Description	Step Description	Steps to produce	Expected Output	Priority	Link	Bug description
001	REG_WCM_ALL-362	001	WCM/REG_WCM_ALL-362	Check Homepage button on Start bar	Step 1: Open control workspace	- Login / - Go to a page (not Home page) / - Click icon on the left to open control workspace	Control workspace is opened, there's Home page button at the bottom	Low	WCM-2807
	REG_WCM_ALL-362	001	WCM/REG_WCM_ALL-362	Check Homepage button on Start bar	Step 2: Check Home page button	Click on Home page button	Jump to Home page	Low	WCM-2807	The Homepage button on Start Bar container moves with the mouse cursor.
002	REG_WCM_CCP-422	001	WCM/REG_WCM_CCP-422	Check when browsing directories with special characters while configuring content detail (IE7)	Step 1: Add category	In IE7 / - Login by admin / - Go to Sites Explorer/acme / - Create category & sub category with names containing characters like the "é"	Create new category successfully	High	WCM-2816
	REG_WCM_CCP-422	001	WCM/REG_WCM_CCP-422	Check when browsing directories with special characters while configuring content detail (IE7)	Step 2: Create new page contain content detail	- Go to Site Editor/Add page wizard / - Input valid values then go to step 3 / - Drag & drop content detail portlet into page	SCV portlet is added into page	High	WCM-2816
	REG_WCM_CCP-422	001	WCM/REG_WCM_CCP-422	Check when browsing directories with special characters while configuring content detail (IE7)	Step 3: Edit content detail	- Click icon to edit content detail portlet / - Choose Select a content / - Browse to select content. Select the previously added directory	Directory is selected	High	WCM-2816	Can not select, there's error in UI
003	REG_WCM_CCP-422	002	WCM/REG_WCM_CCP-422	Check when browsing directories with special characters while configuring CLV (IE7)	Step 1: Add folders	In IE7 / - Login by admin / - Go to Sites Explorer/acme / - Create folder & sub folder with names containing characters like the "é"	Create new folders successfully	High	WCM-2816
	REG_WCM_CCP-422	002	WCM/REG_WCM_CCP-422	Check when browsing directories with special characters while configuring CLV (IE7)	Step 2: Create new page contain CLV	- Go to Site Editor/Add page wizard / - Input valid values then go to step 3 / - Drag & drop CLV portlet into page	CLV portlet is added into page	High	WCM-2816
	REG_WCM_CCP-422	002	WCM/REG_WCM_CCP-422	Check when browsing directories with special characters while configuring CLV (IE7)	Step 3: Edit CLV	- Click icon to edit CLV portlet / - Click Select folder path icon / - Browse to select content. Select the previously added directory	Directory is selected	High	WCM-2816	Can not select, there's error in UI
004	REG_WCM_CCP-405	001	WCM/REG_WCM_CCP-405	Check listing document with special character in name in CLV	Step 1: Go to Sites Explorer	- Login / - Go to Sites Explorer/Sites management/acme/documents	Documents is selected	High	WCM-2795
	REG_WCM_CCP-405	001	WCM/REG_WCM_CCP-405	Check listing document with special character in name in CLV	Step 2: Upload file	Upload a binary with name containing character like '	Upload is done	High	WCM-2795
	REG_WCM_CCP-405	001	WCM/REG_WCM_CCP-405	Check listing document with special character in name in CLV	Step 3: Public uploaded file	- Select to view uploaded file / - Click Manage Publications / - Click on Live to public the file	Uploaded file is changed status	High	WCM-2795
	REG_WCM_CCP-405	001	WCM/REG_WCM_CCP-405	Check listing document with special character in name in CLV	Step 4: Check showing uploaded file	Go to Overview page in acme site	Uploaded file is listed in Documents list with correct name	High	WCM-2795	a %27 replace the '
005	REG_WCM_CCP-424	001	WCM/REG_WCM_CCP-424	Check order content in CLV using manual browse	Step 1: Go to ACME site	- Login by admin / - Select acme site / - Switch to edit mode	Edit mode in acme site is displayed, there's Quick Edit icon for each portlet in the page	High	WCM-2818
	REG_WCM_CCP-424	001	WCM/REG_WCM_CCP-424	Check order content in CLV using manual browse	Step 2: Show form to edit a CLV	Click Quick edit icon at a CLV (e.g: Document)	CLV edit form is shown	High	WCM-2818
	REG_WCM_CCP-424	001	WCM/REG_WCM_CCP-424	Check order content in CLV using manual browse	Step 3: Select document	Choose the manual browse and select a multiple contents for example: / /sites content/live/acme/categories/acme/News1 / /sites content/live/acme/categories/acme/News3 / /sites content/live/acme/categories/acme/News4	Selected documents are listed as 1, 3, 4 in CLV config form	High	WCM-2818
	REG_WCM_CCP-424	001	WCM/REG_WCM_CCP-424	Check order content in CLV using manual browse	Step 4: Change order of document in list	In CLV config form / Use the Up/Down arrows to change their position	The order is changed	High	WCM-2818
	REG_WCM_CCP-424	001	WCM/REG_WCM_CCP-424	Check order content in CLV using manual browse	Step 5: Check listing document after editing the config	Click Save in Edit CLV form	Selected documents are listed as changed at step 4	High	WCM-2818	1. After saving, the order is not respected in the clv display / 2. Edit again and change positions, the problem still occurs.
006	REG_WCM_CCP-429	001	WCM/REG_WCM_CCP-429	Check search when result exceeds 250	Step 1: Add document	- Login / - Go to Site Explorer/Sites Management/acme/documents / - Create/Upload or use web dav to add 250 documents with the same name	250 documents are added	High	WCM-2828
	REG_WCM_CCP-429	001	WCM/REG_WCM_CCP-429	Check search when result exceeds 250	Step 2: Quick Search	- Back to Home page / - Input added file name into search text box & hit enter	Go to Search portlet with search result in pages	High	WCM-2828	- Only the first page results are displayed.
007	REG_WCM_WCM-001	001	WCM/REG_WCM_WCM-001	Check if there's icon to Edit/Delete comment on document	Step 1: Go to Sites Explorer	- Login / - Go to Sites Explorer/Sites Management/acme/document	document folder opened	Low	WCM-2852
	REG_WCM_WCM-001	001	WCM/REG_WCM_WCM-001	Check if there's icon to Edit/Delete comment on document	Step 2: Add document	- Add new document	Add document successfully	Low	WCM-2852
	REG_WCM_WCM-001	001	WCM/REG_WCM_WCM-001	Check if there's icon to Edit/Delete comment on document	Step 3: Add comment	- Select added document / - Click Add Comment / - Input text, click Save	- Comment is added on document / - User who added comment can edit/delete it	Low	WCM-2852
008	REG_WCM_CCP-474	001	WCM/REG_WCM_CCP-474	Check internationalized label in WCMInsertContent functionality	Step 1: Show Add new Free layout webconntent form	- Login / - Go to Site explorer / - Select any driver / - Add new document is Free layout webcontent	Add new free layout content is shown	Low	WCM-2853
	REG_WCM_CCP-474	001	WCM/REG_WCM_CCP-474	Check internationalized label in WCMInsertContent functionality	Step 2: Show Insert content form	Click on the WCMInsertContent icon in the FCKEditor of the main content	Insert content form is shown	Low	WCM-2853
	REG_WCM_CCP-474	001	WCM/REG_WCM_CCP-474	Check internationalized label in WCMInsertContent functionality	Step 3: Change language	- Keep the forms open / - Change displaying language	Labels in form are translated into new selected language	Low	WCM-2853	Labels are not internationalized in the categories' navigation (General drives, There is no content...)
009	REG_WCM_CCP-459	001	WCM/REG_WCM_CCP-459	Check if links Next & Previous in search portlet are internationalized	Step 1: Change language	- Login / - Click icon at the top left of screen & select Language Settings / - Select another language to view page	Page is displayed in new selected language	Low	WCM-2844
	REG_WCM_CCP-459	001	WCM/REG_WCM_CCP-459	Check if links Next & Previous in search portlet are internationalized	Step 2: Search	- Input text into search text box & hit enter	- Search result is returned, all label in result form is translated in current using language (Next & Previous)	Low	WCM-2844	In French, Next & Previous should be: Précédent, Suivant
010	REG_WCM_CCP-454	001	WCM/REG_WCM_CCP-454	Check insert link to a site page when add new web content	Step 1: Add new node	- Login by admin / - Go to Site Editor/Edit navigation / - Right click on blank area and select Add node (to add node at root path) / - Input Node name & do not select any page / - Click Save	New node is added	High	WCM-2843
	REG_WCM_CCP-454	001	WCM/REG_WCM_CCP-454	Check insert link to a site page when add new web content	Step 2: Add sub node	- Right click on new added node & add new sub node with a specific page	Add node with page successfully	High	WCM-2843
	REG_WCM_CCP-454	001	WCM/REG_WCM_CCP-454	Check insert link to a site page when add new web content	Step 3: Add web content	- Go to site explorer / - Select any driver / - Add document is Free layout webcontent / - Input Title and select a layout then click Save	Add new content with corresponding layout form is shown	High	WCM-2843
	REG_WCM_CCP-454	001	WCM/REG_WCM_CCP-454	Check insert link to a site page when add new web content	Step 4: Show form to select link	- In the FCK editor toolbar click on the Insert link to a site page / - Click Get Portal Link	A form to select appears	High	WCM-2843
	REG_WCM_CCP-454	001	WCM/REG_WCM_CCP-454	Check insert link to a site page when add new web content	Step 5: Select page	- Go to path of added node at step 1 & 2	The parent node (without page) is shown but it can not be selected to add into content. Its sub node is listed, the sub node can be added into content	High	WCM-2843
011	REG_WCM_WCM-002	001	WCM/REG_WCM_WCM-002	Check showing Backup path in Manage Publication form	Step 1: Add document	- Login by john / - Go to Sites Explorer/Sites Management/acme/documents / - Click Add document from Action bar / - Input value for fields / - Click Save	New document is added	Low	WCM-2856
	REG_WCM_WCM-002	001	WCM/REG_WCM_WCM-002	Check showing Backup path in Manage Publication form	Step 2: Show Enroll form	- Select to view added document / - Click Manage Publications	Enroll to publication lifecycle from is shown	Low	WCM-2856
	REG_WCM_WCM-002	001	WCM/REG_WCM_WCM-002	Check showing Backup path in Manage Publication form	Step 3: Show Publication form	Click Action icon at the row of Revision	- Manage Publication form is shown / - Backup path is not blank	Low	WCM-2856	Backup path is blank
012	REG_WCM_CCP-453	001	WCM/REG_WCM_CCP-453	Check showing sub node on admin bar when parent does not select to any page	Step 1: Add parent node	- Login by admin / - Go to Site Editor/Edit navigation / - Right click on blank area and select Add node (to add node on root path of current using portal) / - Input Node name & click Save (do not select any page)	Node is added	High	WCM-2842
	REG_WCM_CCP-453	001	WCM/REG_WCM_CCP-453	Check showing sub node on admin bar when parent does not select to any page	Step 2: Add sub node	- Right click on new added node & select Add node / - Input node Name / - Select exiting page for node / - Click Save	New node with page is added	High	WCM-2842
	REG_WCM_CCP-453	001	WCM/REG_WCM_CCP-453	Check showing sub node on admin bar when parent does not select to any page	Step 3: View in admin bar	- Click Save & Finish icon to quit Edit navigation form	- Added nodes (parent & child nodes) are listed in Admin bar	High	WCM-2842	Parent node without page is not shown, so that can not see child node with page
013	REG_WCM_CCP-404	001	WCM/REG_WCM_CCP-404	Check downloading file with name containing an illegal jcr char	Step 1: Upload file	- Login / - Go to Sites Explorer/Site Management/acme/documents / - Upload 1 file with ' in name	Upload is done	Low	WCM-2832
	REG_WCM_CCP-404	001	WCM/REG_WCM_CCP-404	Check downloading file with name containing an illegal jcr char	Step 2: Download file	In the right tree (wcm-view), right click on the Uploaded file and select "Download And Allow Edition"	File is downloaded	Low	WCM-2832	Select "Download And Allow Edition": no response
014	REG_WCM_CCP-404	002	WCM/REG_WCM_CCP-404	Check if labels in right click menu in Sites Explorer are translated	Step 1: Change language	- Login / - Click on Language settings / - Select 1 language to view	Current portal is displayed in new selected language	Low	WCM-2832
	REG_WCM_CCP-404	002	WCM/REG_WCM_CCP-404	Check if labels in right click menu in Sites Explorer are translated	Step 2: Check internationalization label	- Go to Sites Explorer/Sites Management / - Right click on 1 node	All labels are well translated	Low	WCM-2832	"Download And Allow Edition" is not translated
015	REG_WCM_CCP-496	001	WCM/REG_WCM_CCP-496	Check WCMInsertContent when browsing directories with special characters	Step 1: Add folder	- Login / - Goto Sites Explorer → Sites Managemnt → Acme → Documents / - Add new folder with name contain special character (e.g: testé)	New folder is added	High	WCM-2861
	REG_WCM_CCP-496	001	WCM/REG_WCM_CCP-496	Check WCMInsertContent when browsing directories with special characters	Step 2: Upload file	- Select added folder / - Upload 1 image	Upload is done	High	WCM-2861
	REG_WCM_CCP-496	001	WCM/REG_WCM_CCP-496	Check WCMInsertContent when browsing directories with special characters	Step 3: Show add content form	- Go to Home page / - Click Site Editor/Add content / - Select Create new content / - Input title / - Select Free layout webcontent	Add free layout web content form is shown	High	WCM-2861
	REG_WCM_CCP-496	001	WCM/REG_WCM_CCP-496	Check WCMInsertContent when browsing directories with special characters	Step 4: Select content	- In the Fckeditor of this newly added content select WCInsertContent Icon / - Browse General drives → Sites Management → Acme → Documents->testé	Uploaded image is not listed in right pane. It is listed if filter to view by Medias	High	WCM-2861	Error in console / DriverConnector - Error when perform getFoldersAndFiles: <javax.jcr.PathNotFoundException: Item not found /sites content/live/acme/documents/test? in workspac / e collaboration>javax.jcr.PathNotFoundException: Item not found /sites content/live/acme/documents/test? in workspace collaboration
016	REG_WCM_CCP-496	002	WCM/REG_WCM_CCP-496	Check when select drive with special character	Step 1: Add drive	- Login by admin / - Go to Group → Site Administration / - Select Content presentation → Manage Drives / - Click Add Drive / - Input testéDrive for Name / - Select collaboration for Workspace / - Root path for Home path / - Choose Any permission for Permission / - Choose Show side bar option / - Select Admin View and Simple View / - Save	New drive Is added	High	WCM-2861
	REG_WCM_CCP-496	002	WCM/REG_WCM_CCP-496	Check when select drive with special character	Step 2: Add content	- Go to Sites Explorer --> Sites Management / - Select acme → documents / - Click Add document / - Choose Free Layout webcontent template / - In Main content CK: click InsertContent icon / - In the tree explorer select the "testéDrive"	The "testéDrive" is selected properly	High	WCM-2861	Exception in console / [ERROR] DriverConnector - Error when perform getFoldersAndFiles: <java.lang.NullPointerException>java.lang.NullPointerException / at org.exoplatform.wcm.connector.fckeditor.DriverConnector.getFoldersAndFiles(DriverConnector.java:198)
017	REG_WCM_CCP-495	001	WCM/REG_WCM_CCP-495	Check search with accented characters	Step 1: Add document	- Login acme site / - Go to Sites Explorer/Sites Management/acme/documents / - Create new article with word Téléphone	Article is added	High	WCM-2860
	REG_WCM_CCP-495	001	WCM/REG_WCM_CCP-495	Check search with accented characters	Step 2: Public the article	- If there's no Manage Publication in action bar in Site management drive: Go to Sites Administration to Edit Manage Sites drive & Add Admin view / - Select added article / - Click Manage Publication in Action bar & click Live icon to change article status	Article is published	High	WCM-2860
	REG_WCM_CCP-495	001	WCM/REG_WCM_CCP-495	Check search with accented characters	Step 3: Search	Input the word Telephone into search textbox in banner & hit enter	Search result is returned with added article	High	WCM-2860	the article is not mentioned in search result
018	REG_WCM_CCP-418	001	WCM/REG_WCM_CCP-418	Check removing container after being inserted in the page	Step 1: Show edit page form	- Login / - Go to Site Editor → Edit page wizard	Edit page by wizard is show	High	WCM-2821
	REG_WCM_CCP-418	001	WCM/REG_WCM_CCP-418	Check removing container after being inserted in the page	Step 2: Add container into page	- Go to Step 3 of edit page wizard / - Drag & drop a container into page	Container is added into page	High	WCM-2821
	REG_WCM_CCP-418	001	WCM/REG_WCM_CCP-418	Check removing container after being inserted in the page	Step 3: Delete container	- Click x icon at the top right of portlet / - Confirm	The container is removed from page	High	WCM-2821	The newly added container can't be removed from the page. Customer ask for a way to do it.
019	REG_WCM_CCP-514	001	WCM/REG_WCM_CCP-514	Check Edit CLV in manual mode	Step 1: Show edit page form	- Login / - Go to Site Editor → Edit page	Edit page by wizard is show	Low	WCM-2863
	REG_WCM_CCP-514	001	WCM/REG_WCM_CCP-514	Check Edit CLV in manual mode	Step 2: Add CLV into page	- Drag & drop Content List portlet into page	Portlet is added	Low	WCM-2863
	REG_WCM_CCP-514	001	WCM/REG_WCM_CCP-514	Check Edit CLV in manual mode	Step 3: Edit CLV	- Click edit icon to edit added CLV portlet / - Select By content / - Select one content / - Save / - Close	Edit CLV form is closed	Low	WCM-2863
	REG_WCM_CCP-514	001	WCM/REG_WCM_CCP-514	Check Edit CLV in manual mode	Step 4: Edit CLV again	- Click edit icon to edit added CLV portlet / - Click select path icon / - Delete added content / - Save / - Click OK in alert message (requires to select a content) / - Close with the upper-right corner cross / - Click Save / - Click Close	Edit CLV form is closed.	Low	WCM-2863	Issue 1 : the background layer is still there / Issue 2 : the CLV is broken
020	REG_WCM_CCP-403	001	WCM/REG_WCM_CCP-403	Check showing uploaded file with illegal JCR characters in Name in Sites Explorer	Step 1: Upload file	- Go to Group/Sites Explorer / - Select Sites Management drive / - Choose acme/documents / - Click Upload icon in Action bar & select 1 file with name contains illegal JCR characters like ' from your local / - Click Upload icon / - Click Save	File is uploaded	High	WCM-2794
	REG_WCM_CCP-403	001	WCM/REG_WCM_CCP-403	Check showing uploaded file with illegal JCR characters in Name in Sites Explorer	Step 2: View file	Double click on uploaded file to view its content	File is displayed with correct name	High	WCM-2794	The nt:file view is shown and the illegal JCR chars are changed in %number(%27 for ')
021	REG_WCM_WCM-004	001	WCM/REG_WCM_WCM-004	Check when click Edit icon of Content Detail portlet while adding new page	Step 1: Add page	- Login by admin / - Go to Sites Editor → Edit page wizard / - Click Next at step 2 / - Drag & drop Content Detail portlet into page	Portlet is added	High	WCM-2887
	REG_WCM_WCM-004	001	WCM/REG_WCM_WCM-004	Check when click Edit icon of Content Detail portlet while adding new page	Step 2: Edit portlet	- Click edit icon at the top of added portlet	- Edit portlet form is shown	High	WCM-2887	show pop-up message
022	REG_WCM_WCM-005	001	WCM/REG_WCM_WCM-005	Check when drag & drop container into page	Step 1: Edit page	- Login by admin / - Select 1 page / - Select Sites Editor → Edit page wizard / - Click Next to move to step 3	Edit page wizard step 3 is shown	High	WCM-2883
	REG_WCM_WCM-005	001	WCM/REG_WCM_WCM-005	Check when drag & drop container into page	Step 2: Show container	Click Show container icon	Edit page area is shown in container	High	WCM-2883
	REG_WCM_WCM-005	001	WCM/REG_WCM_WCM-005	Check when drag & drop container into page	Step 3: Add container into page	Drag & drop a container into page	The container is added into page area	High	WCM-2883	Blank working area
023	REG_WCM_CCP-443	001	WCM/REG_WCM_CCP-443	Check Content Selector of CLV on IE7	Step 1: Add content	- Login by admin in IE7 / - Go to Sites Explorer → Sites Management → acme → web content / - Add new content, document or upload file	Nodes are added	High	WCM-2835
	REG_WCM_CCP-443	001	WCM/REG_WCM_CCP-443	Check Content Selector of CLV on IE7	Step 2: Add page with CLV portlet	- Click Site Editor --> Create page wizard / - At Step 3: Drag & drop CLV (Content List) portlet into page	Portlet is added	High	WCM-2835
	REG_WCM_CCP-443	001	WCM/REG_WCM_CCP-443	Check Content Selector of CLV on IE7	Step 3: Edit CLV	- Click icon to edit added CLV portlet	Edit CLV form is shown	High	WCM-2835
	REG_WCM_CCP-443	001	WCM/REG_WCM_CCP-443	Check Content Selector of CLV on IE7	Step 4: Config CLV	- Choose Manual mode / - Click Select folder path icon / - In the Content browser tab browse path to added document/web content/uploaded file (General drives → / Sites Management → / Acme → / web contents)	All added document/web content/ uploaded file are listed in right pane	High	WCM-2835
	REG_WCM_CCP-443	001	WCM/REG_WCM_CCP-443	Check Content Selector of CLV on IE7	Step 5: Change the filter	Select Media for filter field	All media files type (upload file, some kinds of document) are listed in right pane by Media filter	High	WCM-2835	NOTHING HAPPENS
024	REG_WCM_CCP-465	001	WCM/REG_WCM_CCP-465	Check Portlet Category Navigation	Step 1: Go to Sites Management	- Login as root. / - Click on "Groups/Site Explorer" on the admin toolbar. / - Click on the "Site Management" drive.	Sites Management drive is displayed	High	WCM-2845
	REG_WCM_CCP-465	001	WCM/REG_WCM_CCP-465	Check Portlet Category Navigation	Step 2: Search	- Type "/acme/categories" at the address bar / - Hit enter	There's acme category in the nodes list	High	WCM-2845
	REG_WCM_CCP-465	001	WCM/REG_WCM_CCP-465	Check Portlet Category Navigation	Step 3: Delete node	- Right click on acme category & select Delete / - Click OK to confirm	acme is deleted	High	WCM-2845
	REG_WCM_CCP-465	001	WCM/REG_WCM_CCP-465	Check Portlet Category Navigation	Step 4: Check after deleting category	Go to News page of acme site	- Check the category is existed or not before trying to access. / - Show the message for user	High	WCM-2845	Exception in console
025	REG_WCM_WCM-003	001	WCM/REG_WCM_WCM-003	Check add new Category in Newsletter Manager	Step 1: Show Newsletter Manager	- Login by admin / - Go to Group/NewsLetter	Newsletter Manager page is shown	Low	WCM-2840
	REG_WCM_WCM-003	001	WCM/REG_WCM_WCM-003	Check add new Category in Newsletter Manager	Step 2: Add new category	- Click Add Category / - Input needed value / - Assign manager:/platform/administrators for Moderator / - Click Save	New category is added	Low	WCM-2840	Error message is shown

				d

				d

				d

## Bugs_v1.6.7
	TEST CASES					Passed	0
				Failed	0
	Function List:	Bugs on WCM 1.2.x for regression test					Blocked	0
	Total Main Cases:	1					Untested	0
				N/A	0
Case No	Related function	Case ID	Path	Case Description	Step Description	Steps to produce	Expected Output	Priority	Link	Bug description
001	REG_WCM_WCM-007	001	WCM/REG_WCM_WCM-007	Check mini calendar when add newsletter	Step 1: Show add new newsletter form	- Login by admin / - Goto Newsletter Manager / - Click New Letter	Add newsletter form Is shown	High	ALL-411
	REG_WCM_WCM-007	001	WCM/REG_WCM_WCM-007	Check mini calendar when add newsletter	Step 2: Check mini calendar	Click on 'Send date' field	Mini calendar is shown properly to select	High	ALL-411	Do not display mini calendar when create newsletter

## Bugs v1.6.8
	TEST CASES					Passed	0
				Failed	0
	Function List:	Bugs on WCM 1.2.x for regression test					Blocked	0
	Total Main Cases:	14					Untested	0
				N/A	0
Case No	Related function	Case ID	Path	Case Description	Step Description	Steps to produce	Expected Output	Priority	Link	Bug description
001	REG_WCM_CCP-404	001	WCM/REG_WCM_CCP-404	Check Download And Allow Edition from right-click menu in right pane on uploaded file with name containing a character like '	Step 1: Upload file	- Go to Sites Explorer/Sites Management/acme/document / - Select wcm-view. / - Upload 1 file with name containing character like '	File is uploaded	High	WCM-2832
	REG_WCM_CCP-404	001	WCM/REG_WCM_CCP-404		Step 2: Show Add category form	- Click + icon at List taxonomy / - Choose Select Category tab (if there's System taxonomy tree as default, you should login by admin, go to Sites Administration → Manage taxonomy → delete system taxonomy tree)	acme taxonomy tree is selected as default, all its taxonomies are listed below	High	WCM-2832	acme taxonomy tree is selected but there's no sub taxonomy is listed
002	REG_WCM_CCP-465	001	WCM/REG_WCM_CCP-465	Check showing News page after deleted acme category	Step 1: Show acme category	- Login by root / - Go to Sites Explorer/Sites Management / - Type "/acme/categories" at the address bar.	acme category is listed	High	WCM-2845
	REG_WCM_CCP-465	001	WCM/REG_WCM_CCP-465		Step 2: Delete acme category	- Right click on acme & select Delete / - Click OK to confirm	acme is deleted	High	WCM-2845
	REG_WCM_CCP-465	001	WCM/REG_WCM_CCP-465		Step 3: View News page	- Go to News page on acme site	News page is displayed & there's no error in console	High	WCM-2845	Error in console
003	REG_WCM_CCP-368	001	WCM/REG_WCM_CCP-368	Check while setting a page with PCLV portlet	Step 1: Show edit page wizard	- Go to ACME site -> Select News page. / - Go to Site Editor ->Edit Page Wizard. / - Go to step 3	Edit page at step 3 is shown in portlet mode	High	WCM-2753
	REG_WCM_CCP-368	001	WCM/REG_WCM_CCP-368		Step 2: Delete PCLV	- Click x icon to delete PCLV portlet (on the right, Category content) / - Click OK to confirm	Portlet is removed from page	High	WCM-2753
	REG_WCM_CCP-368	001	WCM/REG_WCM_CCP-368		Step 3: Delete acme category	Go to Sites Explorer/Sites Management under /acme/categories delete the acme category.	acme category is deleted	High	WCM-2753
	REG_WCM_CCP-368	001	WCM/REG_WCM_CCP-368		Step 4: Re-configure News page	- Select News page / - Go to Site Editor ->Edit Page Wizard. / - Go to step 3 / - Drag drop Category Content into page / - Click Edit icon to edit Category Content portlet	Edit portlet form is shown	High	WCM-2753	Edit form is blank & exception in console
004	REG_WCM_CCP-524	001	WCM/REG_WCM_CCP-524	Check if Link still be referenced after being inserted	Step 1: Show form to add free layout web content	- Go to Sites Explorer/Sites management/acme/document / - Click Add document then select Free layout web content template	Add Free layout web content form is shown	High	WCM-2872
	REG_WCM_CCP-524	001	WCM/REG_WCM_CCP-524		Step 2: Add content	- In the FCK: click Add link to a site page / - Click Get Portal link / - Browse a page / - Save	A link to selected page is added in the content	High	WCM-2872
	REG_WCM_CCP-524	001	WCM/REG_WCM_CCP-524		Step 3: Add more link	- Turn back to the beginning of the current line / - Click on enter 2 times. / - Move the cursor up to the first line / - Click Get Portal link or Insert/edit link / - Browse a page or input a link / - Save	New link is added. There're 2 different links in the content	High	WCM-2872	There's only link added at step 3 with text of the link but the URL is the first added link. The first link was removed.
005	REG_WCM_CCP-668	001	WCM/REG_WCM_CCP-668	Validate page acme/Overview by using W3C Validator	Step 1: Validate page acme/Overview	View source of acme/Overview & put in W3C Validator	No duplicated ID error	High	WCM-2936	Line 2006, column 18: ID "UICLVPortlet" already defined / <div id="UICLVPortlet" class="UICLVPortlet"><span class="UIPopupContain... / Line 2236, column 18: ID "UICLVPortlet" already defined / <div id="UICLVPortlet" class="UICLVPortlet"><span class="UIPopupContain... / Line 2445, column 18: ID "UICLVPortlet" already defined / <div id="UICLVPortlet" class="UICLVPortlet"><span class="UIPopupContain...
006	REG_WCM_CCP-707	001	WCM/REG_WCM_CCP-707	Check translation of Subscribe in French	Step 1: Check translation	- Login / - Go to ACME/Newsletters / - Input email address and Check to subscribe / - Click on Subscribe / - Change language into French	Button: "ChangeSubscriptions" should be "Modifier mon Abonnement"	High	WCM-2952	The label of button has no change
007	REG_WCM_CCP-668	002	WCM/REG_WCM_CCP-668	Check if attribute "target" is in "ACME Overview" when checking with W3C	Step 1: Check Overview page	- Go to ACME Overview / - Validate this page by using W3C validator	Do not throw “there is no attribute "target" “	High	WCM-2939	There is no attribute X: / Line 2110, column 312: there is no attribute "target" / ...acme/documents/conditions.doc" target="_newdoc">Conditions and Requirements</a...
008	REG_WCM_WCM-2929	001	WCM/REG_WCM_WCM-2929	Check if labels in Contact us page are well translated in French	Step 1: Show Contact us page	- Login acme site / - Change language to French / - Click Contact us	- Leave your message -> Laisser votre message / -Select a recipient -> Sélectionner un destinataire / - Your name -> Votre nom / - Your address -> Votre adresse / - Your email address -> Votre adresse d'e-mail / - Your phone number -> Votre numéro de téléphone / - Your message -> Votre message	High	WCM-2929	Label of fields are in English
009	REG_WCM_CCP-704	001	WCM/REG_WCM_CCP-704	Check Content selector form in IE7	Step 1: Show form to add content	- Login in IE7 / - Select Sites Editor/Add content / - Choose Create new content / - Input title then select Free web layout content / - Click Save	Web content form is shown	High	WCM-2951
	REG_WCM_CCP-704	001	WCM/REG_WCM_CCP-704		Step 2: Show form to add content from FCK	In the FCK editor, click Insert Contents icon	Content selector form is shown, the left pane is displayed correctly with all nodes	High	WCM-2951	this window doesn't contain the left part which shows the tree of acessibles drives/directories: the block is empty
010	REG_WCM_CCP-588	001	WCM/REG_WCM_CCP-588	Check when creat page link after adding new page for the user navigation	Step 1: Add new page	- Go to SIte Editor --> Add page wizard / - Choose user:root's navigation / - Put values in fields	New page is created successfully	High	WCM-2914
	REG_WCM_CCP-588	001	WCM/REG_WCM_CCP-588		Step 2: Add new document	- Go to Site Explorer -> Site Management / - Select /acme/web content / - Create 1 Free layout webcontent document / - Insert link to the document	Link is inserted into document	High	WCM-2914	Throw exception
011	REG_WCM_CCP-720	001	WCM/REG_WCM_CCP-720	Check if labels are translated while adding new page by wizard	Step 1: Check page layout list	- Login / - Change language to French / - Click Site Editor/Add page wizard / - Input valid value for step 1 / - Go to step 2 / - Click on the Page configs to the the Page layout drop down list	The list is well translated in French	High	WCM-2957
	REG_WCM_CCP-720	001	WCM/REG_WCM_CCP-720		Step 2: Check translation	- At step 2: select WCM page configs	The list under WCM page configs is shown & well translated in French	High	WCM-2957
	REG_WCM_CCP-720	001	WCM/REG_WCM_CCP-720		Step 3: Check translation	- At step 2: select Column page configs	The list under Column page configs is shown & well translated in French	High	WCM-2957
	REG_WCM_CCP-720	001	WCM/REG_WCM_CCP-720		Step 4: Check translation	- At step 2: select Row page configs	The list under Row page configs is shown & well translated in French	High	WCM-2957
	REG_WCM_CCP-720	001	WCM/REG_WCM_CCP-720		Step 5: Check translation	- At step 2: select Tab page configs	The list under Tab page configs is shown & well translated in French	High	WCM-2957
	REG_WCM_CCP-720	001	WCM/REG_WCM_CCP-720		Step 6: Check translation	- At step 2: select Mix page configs	The list under Mix page configs is shown & well translated in French	High	WCM-2957
012	REG_WCM_CCP-639	001	WCM/REG_WCM_CCP-639	Check the displaying of exo:link when create CLV by Automatic mode	Step 1: Create a content	- Go to SIte Explorer / - Open form to create new webcontent / - Select template: exo:link (Web link)	Web content is created successfully.	High	WCM-2952
	REG_WCM_CCP-639	001	WCM/REG_WCM_CCP-639		Step 2: Check the displaying of exo:link when create CLV by Automatic mode	- Edit CLV page / - Choose Automatic mode / - Open the folder containing that new content	Webcontent is not appeared	High	WCM-2952	Web content appears as a folder.
013	REG_WCM_CCP-731	001	WCM/REG_WCM_CCP-731	Check displaying of invisible page when creating a portal page link into a text	Step 1: Create invisible page	- Go to SIte Editor --> Add page wizard / - At step 1: do not check in “Visible” check-box	Page is created successfully and it is not displayed in navigation	High	WCM-2960
	REG_WCM_CCP-731	001	WCM/REG_WCM_CCP-731		Step 2: Check displaying of invisible page when creating a portal page link into a text	- Go to Site Explorer / - Open form to create “Free layout web content” / - Click on “Insert link to a site page” icon in FCK / - Click on “Get portal link” button	A window is opened. This page selection window allows to select pages with visible and invisible attribute	High	WCM-2960	This page selection window allows to select pages with visible attribute but not invisible ones
014	REG_WCM_CCP-677	001	WCM/REG_WCM_CCP-677	Check displaying .rtf file	Step 1: Open form to upload file	- Login / - Select Site Management drive / - Select /acme/document folder / - Click on “Upload” icon in action bar	“Upload a file” form appears	High	WCM-2943
	REG_WCM_CCP-677	001	WCM/REG_WCM_CCP-677		Step 2: Upload .rtf file	- Browse 1 .rft file / - Click on Upload icon / - Click on Save button	.rft file is uploaded successful	High	WCM-2943
	REG_WCM_CCP-677	001	WCM/REG_WCM_CCP-677		Step 3: View content of .rft file	- Select .rft file above	Content of .rft file is not displayed in the right pane. You can download to view its content.	High	WCM-2943	Error in displaying content.

## Summary_Report
WCM Regression Tests List in AIO					Total cases

Id	Product	Functionality	Bug summary	Product bugID
REG_WCM_CCP-147	WCM	Download	Can not download an uploaded document in PCV portlet	WCM-2157	1	1.6.5	CCP-147
REG_WCM_CCP-346	WCM	Publish	Content edition is not considered after publication	WCM-2727	1		CCP-346
REG_WCM_CCP-345	WCM	Publish	Cache & Categories with publication errors	WCM-2725	1		CCP-345
REG_WCM_CCP-386	WCM	Newsletter	Newsletter mail's validator does not REG_WCM_ALLow a multiple domain names in address mail	WCM-2782	1		CCP-386
REG_WCM_CCP-329	WCM	Publish	IE 7 crash when publishing content after image resize with Shift button pressed	WCM-2715	1		CCP-329
REG_WCM_CCP-384	WCM	CLV	Label categories are not traduced in clv edition	WCM-2781	1		CCP-384
REG_WCM_CCP-247	WCM	Localized content	Patch for "Cannot view localised wcm content ( exo:webcontent .... )"	WCM-2628	1		CCP-247
REG_WCM_CCP-377	WCM	Search	Search result - wrong translation of results' number	WCM-2757	1		CCP-377
REG_WCM_CCP-373	WCM	Search	Search result - wrong traduction when there's no result	WCM-2754	1		CCP-373
REG_WCM_CCP-374	WCM	Form Generator	A bad translation of a label in Form Generator Portlet	WCM-2755	1		CCP-374
REG_WCM_CCP-300	WCM	Language	Mistakes in french internationalization	WCM-2687	1		CCP-300
REG_WCM_CCP-347	WCM	Sorting	Problems with Sorting Mechanism	WCM-2728	1		CCP-347
REG_WCM_CCP-302	WCM	CLV	Taxonomy display error in the CLV categories:encoding problem	WCM-2688 / WCM-2627 / PORTAL-3744	1		CCP-302
REG_WCM_CCP-359	WCM	WCM	Problem with portlet presentation:StringIndexOutOfBoundsException	WCM-2744	1		CCP-359
REG_WCM_CCP-360	WCM	Manage taxonomy	Problem with manage taxonomy	WCM-2745	1		CCP-360
REG_WCM_CCP-368	WCM	PCLV	Error while setting a page with PCLV portlet	WCM-2753	1		CCP-368
REG_WCM_CCP-362	WCM	PCLV	Problem in downloading binary from PCLV	WCM-2746	1		CCP-362
REG_WCM_CCP-332	WCM	WCM	Problem with "Add a site page link " on FCKEDITOR	WCM-2717	1		CCP-332
REG_WCM_CCP-344	WCM	Publish	Publication problems	WCM-2723	1		CCP-344
REG_WCM_CCP-392	WCM	WCM	WCM Content Selector: does not show content of a folder when switchin	WCM-2788	1		CCP-392
REG_WCM_CCP-328	WCM	WCM	Links in viewMode are not underlined	WCM-2227	1		CCP-328
REG_WCM_CCP-371	WCM	CLV	Error when selecting a content in search result tab of CLV	WCM-2751	1		CCP-371
REG_WCM_CCP-343	WCM	CLV	Inversion of content's list in CLV at every validation	WCM-2721	1		CCP-343
REG_WCM_CCP-303	WCM	FCC	Changes in FCC action's parameters are not taken in consideration	WCM-2689 / ECM-5237	1		CCP-303
REG_WCM_CCP-426	WCM	Search	Searched texts in search results are not highlighted	WCM-2822	1		CCP-426
REG_WCM_ALL-362	wCM	wCM	Floating Position of Homepage Button on Start Bar container	WCM-2807	1	1.6.6	ALL-362
REG_WCM_CCP-422	WCM	WCM	A problem with clv when browsing directories with special characters (using IE7)	WCM-2816	2		CCP-422
REG_WCM_CCP-405	WCM	WCM	Problem with displaying documents with name containing illegal JCR characters in PCLV	WCM-2795	1		CCP-405
REG_WCM_CCP-424	WCM	WCM	Can not order content in CLV manual browse	WCM-2818	1		CCP-424
REG_WCM_CCP-429	WCM	WCM	Search's results in FO: Results are not displayed when them number exceeds 250	WCM-2828	1		CCP-429
REG_WCM_WCM-001	WCM	WCM	Can't edit or delete comment	WCM-2852	1		WCM-2852
REG_WCM_CCP-474	WCM	WCM	Labels are not internationalized in WCMInsertContent functionality	WCM-2853	1		CCP-474
REG_WCM_CCP-459	WCM	WCM	Translation of links next and previous in WCM search (FO)	WCM-2844	1		CCP- 459
REG_WCM_CCP-454	WCM	WCM	Problem with FCK editor's insert link to a site page plugin	WCM-2843	1		CCP- 454
REG_WCM_WCM-002	WCM	WCM	Empty backup path at Manage Publication form	WCM-2856	1		WCM-2856
REG_WCM_CCP-483	WCM	WCM	Error when moving document containing illegal jcr characters	WCM-2858	0		CCP-483
REG_WCM_CCP-453	WCM	WCM	the subnodes of nodes that don't have page reference are not shown in the navigation of the WCM site admin toolbar	WCM-2842	1		CCP- 453
REG_WCM_CCP-404	WCM	WCM	Impossible to download a binary file with name containing an illegal jcr char (using the right popup menu)	WCM-2832	2		CCP-404
REG_WCM_CCP-496	WCM	WCM	A problem with WCMInsertContent when browsing directories with special characters	WCM-2861	2		CCP-496
REG_WCM_CCP-495	WCM	WCM	Search does not ignore accented characters	WCM-2860	1		CCP-495
REG_WCM_CCP-418	WCM	WCM	Container can't be removed after being inserted in the page	WCM-2821	1		CCP-418
REG_WCM_CCP-514	WCM	WCM	Broken design with empty CLV in manual mode	WCM-2863	1		CCP-541
REG_WCM_WCM-003	WCM	WCM	Show error message when trying to add new category in Newsletter Manager	WCM-2840	1		CCP-403
REG_WCM_CCP-403	WCM	WCM	Problem for displaying documents with names containing illegal JCR characters using nt:file view	WCM-2794	1		CCP-403
REG_WCM_WCM-004	WCM	WCM	Show pop-up message when click on Edit icon of Content Detail portlet	WCM-2887	1		WCM-2887
REG_WCM_WCM-005	WCM	WCM	Problem when drag & drop container into edit page area	WCM-2883	1		WCM-2840
REG_WCM_CCP-443	WCM	WCM	Content selector does not work on IE7	WCM-2835	1		CCP-443
REG_WCM_WCM-006	WCM	WCM	Not display [Browse] button and upload icon in Illustration Image field in SCV	Portal-3717 / WCM-2327	0		WCM-2883
REG_WCM_CCP-465	WCM	WCM	Portlet Category Navigation	WCM-2845	1		CCP-465
REG_WCM_WCM-007	WCM	WCM	Do not display mini calendar when create newsletter	REG_WCM_ALL-411	1
REG_WCM_CCP-404	WCM	WCM	Download a binary file with name containing an illegal jcr char (using the right popup menu)	WCM-2832	0		CCP-404
REG_WCM_CCP-465	WCM	WCM	Portlet Category Navigation	WCM-2845	0		CCP-465
REG_WCM_CCP-368	WCM	WCM	Error while setting a page with PCLV portlet	WCM-2753	0		CCP-368
REG_WCM_CCP-524	WCM	WCM	Link still be referenced after being inserted	WCM-2872	0		CCP-524
REG_WCM_CCP-668	WCM	WCM	Duplicated portlet ID: Content List, Category Navigation, Category Content, Content by URL	WCM-2936	0		CCP-668
REG_WCM_CCP-707	WCM	Newsletter	Newsletter Wrong text of changing "Subscribe" in French	WCM-2952	0		CCP-707
REG_WCM_CCP-668	WCM	WCM	No attribute "target" in "ACME Overview" when checking with W3C	WCM-2939	0		CCP-668
REG_WCM_WCM-2929	WCM	Language	Hard-coded labels in French	WCM-2929	0
REG_WCM_CCP-704	WCM	WCM	Impossible selection to insert contents into a text content	WCM-2951	0		CCP-704
REG_WCM_CCP-588	WCM	WCM	FCKEditor: Exception when creating page link after adding new page for the user navigation	WCM-2914	0		CCP-558
REG_WCM_CCP-586	WCM	WCM	CLV manual search content: Error when previewing content with image loaded from JCR	WCM-2911	0		CCP-586
REG_WCM_CCP-720	WCM	Language	Add page wizards: Some labels are not translated in French	WCM-2957	0		CCP-720
REG_WCM_CCP-639	WCM	WCM	The selection of repository brings up some content	WCM-2952	0		CCP-639
REG_WCM_CCP-731	WCM	WCM	Impossible to select an invisible page when creating a portal page link into a text (FCK Editor)	WCM-2960	0		CCP-731
REG_WCM_CCP-677	WCM	WCM	Error in displaying .rtf file	WCM-2943	0		CCP-677
Total					50